## Sheet1
Risk Name | Risk Description | Risk Probability of Occurrence % | Risk Impact | Risk Factor | Risk Mitigation | Person in Charge of Tracking
unrealistic estimation | not enough time | 30 | 10 | 3 | smaller goals, work concentrate | Sara
long requirements catalogue | not able to complete all requirements | 30 | 10 | 3 | reduce amount of requirements | Sara
technical impossibilities | difficult to implement | 60 | 6 | 3.6 | find work around | Lior
Staff size and experience | no experience | 50 | 4 | 2 | gain experience | Sara
deficit with external components | not supported tools | 40 | 2 | 0.8 | find work around / use another tool | Damian
development environment | failure of environment | 20 | 10 | 2 | fix it | Damian
Deficit in performance ability of software | slow hardware | 70 | 1 | 0.7 | buy new Hardware | Lior