## Sheet1
Risk Name | Risk Description | Risk Probability of Occurrence % | Risk Impact | Risk Factor | Risk Mitigation | Person in Charge of Tracking
unrealistic estimation | not enough time | 60 | 10 | 6 | smaller goals, work concentrate | together
long requirements catalogue | not able to complete all requirements | 60 | 10 | 6 | reduce amount of requirements | together
technical impossibilities | difficult to implement | 80 | 6 | 4.8 | find work around | together
Staff size and experience | no experience | 70 | 4 | 2.8 | gain experience | together
deficit with external components | not supported tools | 50 | 2 | 1 | find work around / use another tool | together
development environment | failure of environment | 20 | 10 | 2 | fix it | Damian
Deficit in performance ability of software | slow hardware | 80 | 1 | 0.8 | buy new Hardware | Lior